Terms of Reference (ToR)

Development and Validation of Training Modules
JAAGO Foundation Trust

## Document Information

Document Title: Development and Validation of Training Modules

Organization: JAAGO Foundation Trust

Document Type: Terms of Reference (ToR)

Purpose: Develop structured, standardized, and context-appropriate training materials to strengthen the capacity of adolescent girls, service providers, and community stakeholders, promote awareness on gender equality, safeguarding, GBV prevention, and environmental issues, ensure consistency and quality in training delivery, and support long-term sustainability through effective knowledge transfer and community engagement.

## 1. Organizational Background

JAAGO Foundation Trust is a national non-profit organization in Bangladesh committed to improving the lives of disadvantaged communities through education, youth empowerment, skills development, and social inclusion.

JAAGO works with development partners, government institutions, private sector stakeholders, and communities to implement programs in education, youth leadership, gender equality, and climate resilience.

As part of its commitment to strengthening local organizations, JAAGO supports Sports-Based Organizations (SBOs) to enhance institutional capacity, governance, and sustainability.

## 2. Project Overview

The Seashore Girls Empowerment Project focuses on empowering adolescent girls in Cox’s Bazar through sports and life skills development. The project equips girls with skills such as swimming, surfing, and lifeguard training to reduce risks related to gender-based violence and environmental hazards, including drowning.

In collaboration with local schools and community leaders, the project creates safe learning environments where girls can build confidence, leadership, and survival skills.

The project directly reaches around 2,400 adolescents and young people through awareness on youth-friendly services, especially GBV prevention. It also indirectly benefits around 100,000 people through community campaigns on GBV prevention, referral, and reporting mechanisms.

In addition, 150 service providers, including community leaders and local stakeholders, are engaged to promote inclusive and gender-sensitive environments. Sustainability is ensured through continuous engagement with teachers, private sector partners, and community stakeholders through workshops and dialogues on gender norms and climate change awareness.

## 3. Purpose of the Modules

The training modules aim to:

- Develop structured, standardized, and context-appropriate training materials

- Strengthen capacity of adolescent girls, service providers, and community stakeholders

- Promote awareness on gender equality, safeguarding, GBV prevention, and environmental issues

- Ensure consistency and quality in training delivery

- Support long-term sustainability through knowledge transfer and community engagement

## 4. Scope of Work

### Module 1: Environment and Social Standards (ESS)

Purpose:
To integrate Environment and Social Standards into project planning and implementation for sustainable, inclusive, and risk-informed programming.

Content includes:

- ESS principles (environmental protection, inclusion, gender equality, accountability)

- Climate change impacts and coastal disaster risks

- Disaster risk reduction and community resilience

- Water hazards, waste management, pollution prevention

- Ecosystem protection

- Inclusion of marginalized groups (girls, children with disabilities)

- Community participation and accountability

Target group:
Project staff, trainers, learners, parents, teachers, students, government stakeholders, SBOs, community and religious leaders, and coastal communities

### Module 2: Child Protection

Purpose:
To ensure a safe and protective environment for children and adolescents in all project activities.

Content includes:

- Child protection principles

- Types of abuse, exploitation, neglect, violence

- Risks in community and sports-based settings

- Code of conduct

- PSEA (Prevention of Sexual Exploitation and Abuse)

- Reporting and referral mechanisms

Target group: Project staff, trainers, learners, parents, teachers, students, government stakeholders, SBOs, community and religious leaders, and coastal communities

### Module 3: Safeguarding

Purpose:
To ensure safe, respectful, and dignified engagement with all participants, especially children and adolescents.

Content includes:

- Safeguarding principles

- Risk prevention and duty of care

- Professional boundaries and code of conduct

- PSEA standards

- Reporting mechanisms and GRM

- Roles and responsibilities

Target group: Project staff, trainers, learners, parents, teachers, students, government stakeholders, SBOs, community and religious leaders, and coastal communities

### Module 4: Gender-Based Violence (GBV)

Purpose:
To strengthen prevention and response to GBV using a survivor-centered approach.

Content includes:

- Forms and causes of GBV

- Gender inequality and power dynamics

- GBV risks in coastal contexts

- Prevention strategies

- Survivor-centered response principles

- Psychosocial support basics

- Referral pathways

- Coordination and reporting

Target group: Project staff, trainers, learners, parents, teachers, students, government stakeholders, SBOs, community and religious leaders, and coastal communities

## 5. Support from JAAGO Foundation Trust

JAAGO Foundation Trust will provide:

- Relevant project documents and guidelines

- Orientation on project context and target groups

- Technical review and feedback on drafts

- Final approval of all modules

- Ensuring alignment with organizational and donor standards

## 6. Module Design and Printing

- Structured and user-friendly content layout

- Use of illustrations, diagrams, and infographics

- Consistent formatting and professional design

- High-quality printing for field use and training delivery

## 7. Duration and Deliverables

| Deliverable | Description | Timeline |
| --- | --- | --- |
| Inception Report | Methodology, tools, work plan | 20 May 2026 |
| Draft Modules (4) | Full draft with guides | 07 June 2026 |
| Review Report | Consolidated feedback | 10 June 2026 |
| Revised Modules | Updated draft | 14 June 2026 |
| Validation Report | Validation workshop findings | 16 June 2026 |
| Final Modules with design | Approved final version | 18 June 2026 |
| Final Submission Package | All files and reports | 20 June 2026 |

Validity: The assignment will remain valid until 20 June 2026.

## 8. Mode of Payment

Payment will be made upon completion of deliverables. VAT and tax will be applicable as per government rules.

| Deliverable | Description | Payment (%) |
| --- | --- | --- |
| Inception Report | Detailed methodology, work plan, tools, and timeline | - |
| Draft Modules (4) | Full draft with guides | 20% |
| Review Report | Consolidated feedback | – |
| Revised Modules | Updated draft | – |
| Validation Report | Validation workshop findings | 50% |
| Final Modules | Approved final version | – |
| Final Submission Package | Complete set of documents with clean formatting and soft copies | 30% |

## 9. General and Financial Considerations

- All information must be treated as confidential

- JAAGO Foundation Trust will retain ownership of all developed documents

- The consultancy firm must ensure originality and quality of outputs

## 10. Experience / Qualification Required

- Minimum 3-5 years of experience in module or curriculum development

- Experience with NGOs/INGOs

- Knowledge of child rights, empowerment, or education programming

- Ability to develop contextualized training materials

## 11. Ethical Guidelines and Child Protection

All data collection and engagement must follow strict ethical standards:

- Informed consent (including parental consent for minors)

- Confidentiality and anonymity

- Do No Harm principle

- Non-discrimination and respect

- Safeguarding compliance (JAAGO and international standards)

- Safe handling of sensitive topics

- Child-friendly and culturally appropriate approach

- Appropriate and non-invasive questionnaire design

## 12. Risks, Assumptions and Mitigation

Possible risks include delays, confidentiality issues, and stakeholder availability challenges.

Mitigation includes:

- Strong planning and coordination

- Timely communication

- Strict data protection

- Adherence to timelines

## 13. Safeguarding and PSEA

The consultant/firm must strictly follow JAAGO Safeguarding Policy and PSEA standards.

This includes:

- Protection of children and vulnerable groups

- Ethical engagement

- Immediate reporting of concerns

- Compliance with safeguarding frameworks

Non-compliance may lead to contract termination.

## 14. Contact Person

Md. Zahid Hossain
Program Coordinator, Shopner Sharothi Project, JAAGO Foundation Trust
📧 mohammad.zahid@jaago.com.bd

## 15. Application Procedure

Interested candidates/consultancy firms are requested to submit technical and financial proposals.

📅 Deadline: 07 May 2026
📧 Email: procurement.jft@jaago.com.bd

Late submissions will not be considered.